## Plan
There are 50 days left until assignment submission					Non Teaching Weeks					Pandas Lecture					Assignment

	planned
	complete	MCQ Test – Computer Architecture & Technology Convergence					Pands Problem Sheet Due on 14/04/2023					MCQ Test – Computer Architecture & Technology Convergence					Baby Due					Due
	delayed	Week 1 of 8					Week 2 of 8					Week 3 of 8					Week 4 of 8					Week 5 of 8					Week 6 0f 8					Week 7 of 8					Week 8 of 8
		Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday	Saturday	Sunday	Monday	Tuesday	Wednesday	Thursday	Friday
	Deliverable	3/20/2023	3/21/2023	3/22/2023	3/23/2023	3/24/2023	3/25/2023	3/26/2023	3/27/2023	3/28/2023	3/29/2023	3/30/2023	3/31/2023	4/1/2023	4/2/2023	4/3/2023	4/4/2023	4/5/2023	4/6/2023	4/7/2023	4/8/2023	4/9/2023	4/10/2023	4/11/2023	4/12/2023	4/13/2023	4/14/2023	4/15/2023	4/16/2023	4/17/2023	4/18/2023	4/19/2023	4/20/2023	4/21/2023	4/22/2023	4/23/2023	4/24/2023	4/25/2023	4/26/2023	4/27/2023	4/28/2023	4/29/2023	4/30/2023	5/1/2023	5/2/2023	5/3/2023	5/4/2023	5/5/2023	5/6/2023	5/7/2023	5/8/2023	5/9/2023	5/10/2023	5/11/2023	5/12/2023
1	Create Repo On Git Hub	30 mins
1.01	Create git ignore	10 mins
1.02	Create README.md template	10 mins
1.03	Create analysis.py empty file	10 mins
1.04	Commit to GitHub	10 mins

2	Download IRIS Data Set			10 mins

3	Plan
3.01	Create plan			3 hrs
3.02	Update plan					5 mins	5 mins	5 mins	5 mins

4	README.md
4.01	Create Headings			30 mins
4.02	Write Description					25 mins
4.03	Write Background					25 mins	25 mins	1 hr
4.04	Write Discussion					1 hr
4.05	Update Headings
4.051	Definitions					10 min		10 min					20 min
4.052	References					10 min		10 min					20 min
4.053	Update links					10 min		10 min					20 min

5	Research			3 hrs
5.01	Research background			1 hr
5.02	Research existing analysis & scripts			2 hrs

6	analysis.py
6.01	Read in source data from data set
6.011	Create code					20 mins
6.012	Update commentary					10 min
6.013	Test					10 mins
6.014	Debug					20 mins
6.015	Sign Off					5 mins
6.02	Script basic analysis
6.021	Create code					3 hrs
6.022	Update commentary					20 mins
6.023	Test					20 mins
6.024	Debug					20 mins
6.025	Sign Off					20 mins
6.03	Script detailed analysis
6.031	Create code					1 hr	1 hr	1 hr	3 hrs
6.032	Update commentary					40 min
6.033	Test					40 min
6.034	Debug					40 min
6.035	Sign Off					40 min

	Submit